## Task_List
Task No | Type | Description | Assigned to
Task 1: |  | Copy “ card_transactions.csv” file from local system to HDFS. | Bhanu/Ganesh
Task 2: | Table creation | Create the “ card_transactions” table in MySQL based on the card_transactions.csv file structure. | Bhanu/Ganesh
Task 3: |  | Do a sqoop export to the database for card_transactions.csv and delete the file from HDFS. | Bhanu/Ganesh
Task 4: | Table creation | On “member_score” and “member_details” create a normal hive external table. | Bhanu/Nalini
Task 5: | Table creation | Create a special “card_transactions” Hbase table managed by Hive. | Bhanu/Nalini
Task 6: | Table creation | Create a Hbase “lookup” table with columns - member_id, card_id, UCL, timestamp, zipcode, credit_score. | Bhanu/Nalini
Task 7: | Batch Processing | Sqoop import member_score from AWS-RDS to Hive. (Full load import, has to be refreshed every week) | Bhanu/Nalini
Task 8: | Batch Processing | Sqoop import member_details from AWS-RDS to Hive. (Incremental load import in append mode based on member_id for every 8hrs) | Bhanu/Nalini
Task 9: | Batch Processing | Sqoop import card_transactions to HDFS from MySQL. (This is a one-time full load activity. The card_transactions table will be updated with new transactions while in streaming mode.) | Bhanu/Ganesh
Task 10: | Scheduling | Schedule a sqoop import job using Airflow to import member_score from AWS-RDS to Hive on a full-load. | Bhanu/Nalini
Task 11: | Scheduling | Schedule a sqoop import job using Airflow to import member_details from AWS-RDS to Hive on an incremental append mode for every 8hrs. | Bhanu/Nalini
Task 12: | Spark-HBase Integration | 1. For populating the card_transactions table. 2. For populating the look_up table. | Ganesh/Nalini
Task 13: | Spark-Hive Integration | Spark-Hive Integration for spark stream processing. | Bhanu
Task 14: | Spark-Hive Integration | Access the hive tables using apache spark and calculate the UCL. | Bhanu
Task 15: | Kafka Streaming | Producer to create the transactions in JSON format, to be added and queued in Kafka topics. | Bhanu/Ganesh
Task 16: | Spark Streaming | Spark structured streaming program as a Consumer that will consume the data from the kafka topics. | Bhanu
Task 17: | Spark Processing | Retrieve the timestamp and zipcode of the last transaction of each card. | Ganesh/Nalini
Task 18.1 | Spark Processing | Validating RULE 1 -> “credit_score > 200” | Ganesh/Nalini
Task 18.2 | Spark Processing | Validating RULE 2 -> “transaction amount <= UCL” | Ganesh/Nalini
Task 18.3 | Spark Processing | Validating RULE 3 -> “zipcode distance within threshold” | Ganesh/Nalini
Task 19: | Spark Processing | Based on the above rules, the entire transaction along with status should be updated in the card_transactions table. | Ganesh/Nalini
Task 20: | Spark Processing | Schedule a job for validating rules by comparing the incoming data from the POS terminals in JSON format with the values in the lookup table. | Ganesh/Nalini
Task 21: | Spark Processing | If the transaction was marked genuine, then we need to update the lookup table with the new timestamp and the zipcode. | Ganesh/Nalini
Task 22: | Airflow | Schedule a job for populating the lookup table. | Ganesh/Nalini